## Sheet1
ID | Related Task | Risk Description | Likelihood | Impact | Risk Level | Explanation | Mitigation Strategy | Responsible
R1 | Searching on additional joke datasets | Difficulty in finding high-quality, clean, and ethically appropriate joke datasets. | Medium | High | High | Most public datasets may be low-quality, outdated, or contain inappropriate content. Licensing can also be a problem. | Broaden the search scope (Kaggle, Hugging Face, academic corpora). Consider manual collection if needed. | Berkay
R2 | Clean and preprocess data | Important joke content may be accidentally deleted or corrupted during preprocessing. | Medium | Medium | Medium | Removing duplicates or offensive content may remove unique variations. Encoding and punctuation issues may also arise. | Always back up original data. Test preprocessing on samples before applying to the whole set. Log each step. | Eren
R3 | What is Hugging Face? Why we decided to use it? | Some models or features may become paid or unavailable due to Hugging Face policy changes. | Low | Medium | Low-Medium | Changes in access or usage policy may delay progress during model usage. | Keep backup options ready (OpenLLM, TensorFlow Hub). Document Hugging Face alternatives. | İpek
R4 | How we will categorize jokes (by topic, humor type, etc.) | Categories may be too subjective or jokes may belong to multiple categories. | Medium | High | High | Overlap like “Nasreddin Hoca” vs. “Crazy” jokes may confuse models or annotators. | Define categories clearly. Use annotation guidelines. Run test labeling and adjust with feedback. | Ethem
R5 | Which model we will select from Hugging Face platform? | Chosen model may have low accuracy or may be too slow for real-time inference. | Medium | High | High | Some transformer models are heavy, slow, or not well-trained on Turkish data. | Benchmark at least 3 models. Compare speed and accuracy. Verify CPU/GPU compatibility. | Seyda
R6 | Finding and analyzing similar examples of the project & editing resources file | Limited access to up-to-date or directly relevant project examples. | Low | Medium | Low | Humor classification in Turkish or fıkra-specific tasks may be rare in research. | Do a thorough search on GitHub, ArXiv, Google Scholar. Focus on multilingual projects as well. | Muharrem