## Sheet1
Görev Adı | Başlangıç Tarihi | Bitiş Tarihi | Süre (gün)
Research joke datasets (databases, web scraping, existing datasets) | 6 Mart 2025 | 20 Mart 2025 | 15
Define project goals (What type of jokes will the LLM generate?...) | 6 Mart 2025 | 20 Mart 2025 | 15
Explore Project Requirements | 6 Mart 2025 | 20 Mart 2025 | 15
Searching on additional joke datasets | 20 Mart 2025 | 10 Nisan 2025 | 21
Clean and preprocess data (remove duplicates, offensive content, etc.) | 20 Mart 2025 | 10 Nisan 2025 | 21
What is Hugging Face? Why use it? Creating Risk Table | 20 Mart 2025 | 10 Nisan 2025 | 21
Categorize jokes (by length, topic, humor type...) | 20 Mart 2025 | 10 Nisan 2025 | 21
Model selection from Hugging Face | 7 Nisan 2025 | 9 Nisan 2025 | 3
Creating database of the website | 10 Nisan 2025 | 24 Nisan 2025 | 15
Training the model | 10 Nisan 2025 | 24 Nisan 2025 | 15
UI/UX Design of the Website | 10 Nisan 2025 | 24 Nisan 2025 | 15
Website backend code | 10 Nisan 2025 | 24 Nisan 2025 | 15
Applying the UI design to the codebase | 10 Nisan 2025 | 24 Nisan 2025 | 15
Implement the model to website & create LLM from scratch | 24 Nisan 2025 | 8 Mayıs 2025 | 15
UI Improvements | 24 Nisan 2025 | 8 Mayıs 2025 | 15
Duration Table (oluşturma veya güncelleme) | 24 Nisan 2025 | 8 Mayıs 2025 | 15
Putting all system architecture together | 24 Nisan 2025 | 8 Mayıs 2025 | 15
Scratch model improvement & comparison | 8 Mayıs 2025 | 22 Mayıs 2025 | 15
Creating presentation context | 8 Mayıs 2025 | 22 Mayıs 2025 | 15
Presentation visualization (2 kart) | 8 Mayıs 2025 | 22 Mayıs 2025 | 15
Working on additional website features | 8 Mayıs 2025 | 22 Mayıs 2025 | 15
UI Details | 8 Mayıs 2025 | 22 Mayıs 2025 | 15